## Slide 1
SSPM Initiative | SSPM Integration — Summary Dashboard
UNIQUE APPLICATIONS — BY PRIORITY TIER
All Tiers
88
22 in-scope
IN SCOPE
P1
8
Unique Apps
5 done · 3 pending
IN SCOPE
P2
14
Unique Apps
8 done · 6 pending
OUT OF SCOPE
P3
30
Unique Apps
0 done · 30 pending
OUT OF SCOPE
P4
20
Unique Apps
0 done · 20 pending
OUT OF SCOPE
P5
16
Unique Apps
0 done · 16 pending
INSTANCES — PROD & NON-PROD ONBOARDING STATUS
Tier
Prod Instances
Completed
Pending
Total
Non-Prod Instances
Completed
Pending
Total
Grand Total
Instances
Done
P1
8
3
11
3
2
5
16
11
P2
12
8
20
4
6
10
30
16
P3
8
22
30
N/A
N/A
N/A
30+
8
P4
4
16
20
N/A
N/A
N/A
20+
4
P5
0
15
15
N/A
N/A
N/A
15+
0
TOTAL
32
64
96
7
8
15
111
39
What is a Unique Application?
A Unique Application is a distinct SaaS product registered in the SSPM programme — e.g. Salesforce, Workday. It is counted once regardless of how many environments or regions it operates in.
Example: Salesforce = 1 unique app, even if it has multiple regional tenants.
What is an Instance?
An Instance is a specific deployment of an app — a particular environment (Prod or Non-Prod) or tenant. One app can have multiple instances, each onboarded into SSPM separately.
Example: Salesforce has 3 instances — APAC Prod, EMEA Prod, AMER Non-Prod.
● Completed
● Pending
● N/A — Non-Prod visibility not available for P3/P4/P5
[ Add your org footer here ]

## Slide 2
SSPM Initiative | Integration Status — Region-wise Summary
INSTANCE ONBOARDING STATUS BY REGION — PROD & NON-PROD
Region
Prod Instances
Completed
Pending
Total
Non-Prod Instances
Completed
Pending
Total
Grand Total
Instances
Done
APAC
10
8
18
3
4
7
25
13
EMEA
7
6
13
2
3
5
18
9
Global
5
3
8
N/A
N/A
N/A
8
5
Japan
3
2
5
1
1
2
7
4
North America
4
5
9
0
3
3
12
4
TG
2
3
5
0
1
1
6
2
TOTAL
31
27
58
6
12
18
76
37
● Completed
● Pending
N/A — No Non-Prod environment
[ Add your org footer here ]

## Slide 3
SSPM Initiative | P1 Applications — Integration Status
P1 · 8 Apps
Instance Coverage
PROD
8/11
NON-PROD
3/5
● Completed
● In Progress
● Not Started
Status
PROD
NON-PROD
A1
In Progress
PROD 2/3
NP 1/2
A2
Completed
PROD 1/1
NP 1/1
A3
Completed
PROD 1/1
—
A4
In Progress
PROD 1/1
NP 0/1
A5
Completed
PROD 1/1
—
A6
Completed
PROD 1/1
NP 1/1
A7
In Progress
PROD 1/2
—
A8
Not Started
PROD 0/1
—
[ Add your org footer here ]

## Slide 4
SSPM Initiative | P2 Applications — Integration Status
P2 · 14 Apps
Instance Coverage
PROD
6/14
NON-PROD
1/10
● All Done
● Partial
● Not Started
A1
PROD 1/1 ✓
NP 0/1 ○
A2
PROD 1/1 ✓
NP 0/2 ○
A3
PROD 1/1 ✓
NP 1/1 ✓
A4
PROD 1/1 ✓
NP 0/1 ○
A5
PROD 0/1 ○
NP 0/1 ○
A6
PROD 0/1 ○
NP —
A7
PROD 0/1 ○
NP 0/1 ○
A8
PROD 0/1 ○
NP 0/1 ○
A9
PROD 1/1 ✓
NP 0/1 ○
A10
PROD 0/1 ○
NP —
A11
PROD 1/1 ✓
NP 0/1 ○
A12
PROD 0/1 ○
NP —
A13
PROD 0/1 ○
NP —
A14
PROD 0/1 ○
NP —
[ Add your org footer here ]

## Slide 5
SSPM Initiative | Milestone Roadmap & Out-of-Scope Overview
Tier
Total Apps
Prod Completed
Prod Pending
Non-Prod
P3
~30
8
~22
N/A — Visibility Pending
P4
~20
4
~16
N/A — Visibility Pending
P5
~15
0
~15
N/A — Visibility Pending
Phase 2 · Auto-Ticketing Integration
In Progress
1
SSPM → ServiceNow connector design & build
In Progress
2
Ticket template, SLA & assignment routing
Not Started
3
UAT, pilot & go-live
Not Started
Phase 3 · Scorecard & Operationalisation
Not Started
1
Define KPIs, scoring framework & dashboard
Not Started
2
Runbook, SOP & SSPM operating model (BAU)
Not Started
3
App owner reporting cadence & BAU handover
Not Started
[ Add your org footer here ]

## Slide 6
SSPM Initiative | Blockers & Impediments
🚧 P1 Integration Blockers
B1
A1 — Prod instance access provisioning pending IT approval
Owner: IT Ops
High
B2
A7 — Prod instance API unreachable, firewall change raised
Owner: Network
High
B3
A4 — Non-Prod tenant config not shared by app owner
Owner: App Owner
Med
🚧 Milestone & Phase Blockers
B1
A1 (P1) — Prod instance access provisioning pending IT Ops approval
Phase 1
Owner: IT Ops
High
B2
A7 (P1) — Prod instance API unreachable, firewall change raised
Phase 1
Owner: Network
High
B3
ServiceNow connector design blocked — ITSM team bandwidth
Phase 2
Owner: ITSM Team
High
B4
Scorecard KPI framework pending Security Architecture approval
Phase 3
Owner: Sec Arch
Med
[ Add your org footer here ]

## Slide 7
SSPM Initiative | P1 Apps — Security Score Improvement (Last 3 Months)
Each pane shows the score trend for one P1 app over Month 1 → Month 2 → Month 3.
A1
Month 1
Month 2
Month 3
📷 Paste screenshot of A1 score trend here
A2
Month 1
Month 2
Month 3
📷 Paste screenshot of A2 score trend here
A3
Month 1
Month 2
Month 3
📷 Paste screenshot of A3 score trend here
A4
Month 1
Month 2
Month 3
📷 Paste screenshot of A4 score trend here
A5
Month 1
Month 2
Month 3
📷 Paste screenshot of A5 score trend here
A6
Month 1
Month 2
Month 3
📷 Paste screenshot of A6 score trend here
A7
Month 1
Month 2
Month 3
📷 Paste screenshot of A7 score trend here
A8
Month 1
Month 2
Month 3
📷 Paste screenshot of A8 score trend here
[ Add your org footer here ]