## Slide 1
SSPM Initiative | SSPM Integration — Summary Dashboard
UNIQUE APPLICATIONS — BY PHASE
All Phases
573
Applications
50 in-scope
621 instances
IN SCOPE
P1
18
Unique Apps
22
Done
10
In Prog
9
Not Strt
2
Future
3
D-Scoped
IN SCOPE
P2
32
Unique Apps
7
In Prog
36
Not Strt
6
Future
3
D-Scoped
OUT OF SCOPE
P3
143
Unique Apps
12
Done
131
Not Strt
OUT OF SCOPE
P4
198
Unique Apps
4
Done
194
Not Strt
OUT OF SCOPE
P5
182
Unique Apps
182
Not Strt
INSTANCES — PROD & NON-PROD ONBOARDING STATUS
Phase
Prod Instances
Completed
Pending
Total
Non-Prod Instances
Completed
Pending
Total
Grand Total
Instances
Done
P1
25
21
46
9
18
27
73
34
P2
7
45
52
0
26
26
78
7
P3
12
131
143
N/A
N/A
N/A
143
12
P4
4
194
198
N/A
N/A
N/A
198
4
P5
0
182
182
N/A
N/A
N/A
182
0
TOTAL
48
573
621
9
44
53
674
57
What is a Unique Application?
A Unique Application is a distinct SaaS product in the SSPM programme (e.g. Salesforce, Workday). Counted once regardless of how many environments or regions it operates in.
Example: Salesforce = 1 unique app, even with 8 regional instances.
What is an Instance?
An Instance is one JIRA Story representing a specific deployment — a regional environment (Prod or Non-Prod) or tenant. One app can have multiple instances, each onboarded into SSPM separately.
Example: Salesforce has 8 instances — APAC Prod, EMEA Prod, NA Sandbox …
● Done
● In Prog
● Not Strt
● Future
● D-Scoped
[ Add your org footer here ]

## Slide 2
SSPM Initiative | Integration Status — Region-wise Summary
INSTANCE ONBOARDING STATUS BY REGION — PROD & NON-PROD
Region
Prod Instances
Completed
Pending
Total
Non-Prod Instances
Completed
Pending
Total
Grand Total
Instances
Done
APAC
15
20
35
6
17
23
58
21
EMEA
5
9
14
1
10
11
25
6
Global
6
13
19
0
4
4
23
6
Japan
3
1
4
1
0
1
5
4
North America
3
22
25
1
13
14
39
4
TG
0
1
1
N/A
N/A
N/A
1
0
TOTAL
32
66
98
9
44
53
151
41
● Completed
● Pending
N/A — No Non-Prod environment
[ Add your org footer here ]

## Slide 3
SSPM Initiative | Phase 1 Applications — Integration Status
P1 · Pg 1/3
Instance Coverage
PROD
25/46
NON-PROD
9/27
App Status Breakdown
4 Done
8 In Prog
4 Not Strt
2 Future
#
Application · Org / Prod / Non-Prod Instances
Status
PROD
NON-PROD
1
Salesforce
×8 Instance
×8 Prod
×6 Non-Prod
Onboarding In Progress
PROD 5/8
NP 2/6
2
Workday
×3 Instance
×3 Prod
×3 Non-Prod
Onboarding In Progress
PROD 2/3
NP 1/3
3
ServiceNow
×4 Instance
×4 Prod
×3 Non-Prod
Onboarding In Progress
PROD 3/4
NP 1/3
4
GitHub Enterprise
×3 Instance
×3 Prod
×3 Non-Prod
Not Started
PROD 2/3
NP 2/3
5
Microsoft 365
×5 Instance
×5 Prod
×0 Non-Prod
Onboarding In Progress
PROD 3/5
—
6
Okta
×3 Instance
×3 Prod
×3 Non-Prod
Onboarding In Progress
PROD 2/3
NP 2/3
NOTE
Status Grouping: Completed = 'Completed' + 'De-Scoped' (shown in green). Pending = 'Onboarding In Progress' + 'Not Started' + 'Future Request' (shown with their respective colour). Status is determined by the JIRA dropdown field configured in config.py → STATUS_FIELD.
[ Add your org footer here ]

## Slide 4
SSPM Initiative | Phase 1 Applications — Integration Status
P1 · Pg 2/3
Instance Coverage
PROD
25/46
NON-PROD
9/27
App Status Breakdown
4 Done
8 In Prog
4 Not Strt
2 Future
#
Application · Org / Prod / Non-Prod Instances
Status
PROD
NON-PROD
7
Zoom
×2 Instance
×2 Prod
×1 Non-Prod
Not Started
PROD 1/2
NP 0/1
8
Slack
×2 Instance
×2 Prod
×1 Non-Prod
Onboarding In Progress
PROD 1/2
NP 0/1
9
Palo Alto Prisma
×2 Instance
×2 Prod
×2 Non-Prod
Completed
PROD 2/2
NP 1/2
10
CrowdStrike
×1 Instance
×1 Prod
×1 Non-Prod
Onboarding In Progress
PROD 1/1
NP 0/1
11
Proofpoint
×3 Instance
×3 Prod
×0 Non-Prod
Completed
PROD 2/3
—
12
Mimecast
×2 Instance
×2 Prod
×2 Non-Prod
Onboarding In Progress
PROD 0/2
NP 0/2
NOTE
Status Grouping: Completed = 'Completed' + 'De-Scoped' (shown in green). Pending = 'Onboarding In Progress' + 'Not Started' + 'Future Request' (shown with their respective colour). Status is determined by the JIRA dropdown field configured in config.py → STATUS_FIELD.
[ Add your org footer here ]

## Slide 5
SSPM Initiative | Phase 1 Applications — Integration Status
P1 · Pg 3/3
Instance Coverage
PROD
25/46
NON-PROD
9/27
App Status Breakdown
4 Done
8 In Prog
4 Not Strt
2 Future
#
Application · Org / Prod / Non-Prod Instances
Status
PROD
NON-PROD
13
Qualys
×1 Instance
×1 Prod
×0 Non-Prod
Completed
PROD 1/1
—
14
Rapid7
×2 Instance
×2 Prod
×0 Non-Prod
Not Started
PROD 0/2
—
15
Tenable
×1 Instance
×1 Prod
×0 Non-Prod
Future Request
PROD 0/1
—
16
Varonis
×1 Instance
×1 Prod
×0 Non-Prod
Completed
PROD 0/1
—
17
SailPoint
×2 Instance
×2 Prod
×2 Non-Prod
Future Request
PROD 0/2
NP 0/2
18
BeyondTrust
×1 Instance
×1 Prod
×0 Non-Prod
Not Started
PROD 0/1
—
NOTE
Status Grouping: Completed = 'Completed' + 'De-Scoped' (shown in green). Pending = 'Onboarding In Progress' + 'Not Started' + 'Future Request' (shown with their respective colour). Status is determined by the JIRA dropdown field configured in config.py → STATUS_FIELD.
[ Add your org footer here ]

## Slide 6
SSPM Initiative | Phase 2 Applications — Integration Status
P2 · Pg 1/6
Instance Coverage
PROD
7/52
NON-PROD
0/26
App Status Breakdown
2 Done
7 In Prog
18 Not Strt
5 Future
#
Application · Org / Prod / Non-Prod Instances
Status
PROD
NON-PROD
1
Box
×3 Instance
×3 Prod
×3 Non-Prod
Onboarding In Progress
PROD 1/3
NP 0/3
2
Dropbox
×2 Instance
×2 Prod
×0 Non-Prod
Not Started
PROD 0/2
—
3
Atlassian (Jira/Confluence)
×3 Instance
×3 Prod
×3 Non-Prod
Onboarding In Progress
PROD 1/3
NP 0/3
4
Zendesk
×2 Instance
×2 Prod
×1 Non-Prod
Not Started
PROD 0/2
NP 0/1
5
DocuSign
×2 Instance
×2 Prod
×2 Non-Prod
Onboarding In Progress
PROD 1/2
NP 0/2
6
HubSpot
×2 Instance
×2 Prod
×1 Non-Prod
Not Started
PROD 0/2
NP 0/1
NOTE
Status Grouping: Completed = 'Completed' + 'De-Scoped' (shown in green). Pending = 'Onboarding In Progress' + 'Not Started' + 'Future Request' (shown with their respective colour). Status is determined by the JIRA dropdown field configured in config.py → STATUS_FIELD.
[ Add your org footer here ]

## Slide 7
SSPM Initiative | Phase 2 Applications — Integration Status
P2 · Pg 2/6
Instance Coverage
PROD
7/52
NON-PROD
0/26
App Status Breakdown
2 Done
7 In Prog
18 Not Strt
5 Future
#
Application · Org / Prod / Non-Prod Instances
Status
PROD
NON-PROD
7
Tableau / Salesforce Analytics
×3 Instance
×3 Prod
×2 Non-Prod
Onboarding In Progress
PROD 1/3
NP 0/2
8
Coupa
×2 Instance
×2 Prod
×1 Non-Prod
Not Started
PROD 0/2
NP 0/1
9
Snowflake
×2 Instance
×2 Prod
×2 Non-Prod
Not Started
PROD 0/2
NP 0/2
10
Splunk
×1 Instance
×1 Prod
×1 Non-Prod
Onboarding In Progress
PROD 1/1
NP 0/1
11
Ariba / SAP
×2 Instance
×2 Prod
×2 Non-Prod
Not Started
PROD 0/2
NP 0/2
12
Veeva Vault
×2 Instance
×2 Prod
×0 Non-Prod
Future Request
PROD 0/2
—
NOTE
Status Grouping: Completed = 'Completed' + 'De-Scoped' (shown in green). Pending = 'Onboarding In Progress' + 'Not Started' + 'Future Request' (shown with their respective colour). Status is determined by the JIRA dropdown field configured in config.py → STATUS_FIELD.
[ Add your org footer here ]

## Slide 8
SSPM Initiative | Phase 2 Applications — Integration Status
P2 · Pg 3/6
Instance Coverage
PROD
7/52
NON-PROD
0/26
App Status Breakdown
2 Done
7 In Prog
18 Not Strt
5 Future
#
Application · Org / Prod / Non-Prod Instances
Status
PROD
NON-PROD
13
Workiva
×1 Instance
×1 Prod
×0 Non-Prod
Not Started
PROD 0/1
—
14
NetSuite
×2 Instance
×2 Prod
×0 Non-Prod
Not Started
PROD 0/2
—
15
Anaplan
×1 Instance
×1 Prod
×0 Non-Prod
Future Request
PROD 0/1
—
16
Concur (SAP)
×1 Instance
×1 Prod
×0 Non-Prod
Not Started
PROD 0/1
—
17
Adobe Sign
×2 Instance
×2 Prod
×2 Non-Prod
Not Started
PROD 0/2
NP 0/2
18
SuccessFactors
×2 Instance
×2 Prod
×0 Non-Prod
Not Started
PROD 0/2
—
NOTE
Status Grouping: Completed = 'Completed' + 'De-Scoped' (shown in green). Pending = 'Onboarding In Progress' + 'Not Started' + 'Future Request' (shown with their respective colour). Status is determined by the JIRA dropdown field configured in config.py → STATUS_FIELD.
[ Add your org footer here ]

## Slide 9
SSPM Initiative | Phase 2 Applications — Integration Status
P2 · Pg 4/6
Instance Coverage
PROD
7/52
NON-PROD
0/26
App Status Breakdown
2 Done
7 In Prog
18 Not Strt
5 Future
#
Application · Org / Prod / Non-Prod Instances
Status
PROD
NON-PROD
19
Darktrace
×1 Instance
×1 Prod
×1 Non-Prod
Onboarding In Progress
PROD 1/1
NP 0/1
20
Elastic (ELK)
×1 Instance
×1 Prod
×1 Non-Prod
Not Started
PROD 0/1
NP 0/1
21
PagerDuty
×1 Instance
×1 Prod
×0 Non-Prod
Future Request
PROD 0/1
—
22
Dynatrace
×2 Instance
×2 Prod
×2 Non-Prod
Not Started
PROD 0/2
NP 0/2
23
Miro
×1 Instance
×1 Prod
×0 Non-Prod
Completed
PROD 0/1
—
24
Figma
×1 Instance
×1 Prod
×0 Non-Prod
Not Started
PROD 0/1
—
NOTE
Status Grouping: Completed = 'Completed' + 'De-Scoped' (shown in green). Pending = 'Onboarding In Progress' + 'Not Started' + 'Future Request' (shown with their respective colour). Status is determined by the JIRA dropdown field configured in config.py → STATUS_FIELD.
[ Add your org footer here ]

## Slide 10
SSPM Initiative | Phase 2 Applications — Integration Status
P2 · Pg 5/6
Instance Coverage
PROD
7/52
NON-PROD
0/26
App Status Breakdown
2 Done
7 In Prog
18 Not Strt
5 Future
#
Application · Org / Prod / Non-Prod Instances
Status
PROD
NON-PROD
25
Notion
×1 Instance
×1 Prod
×0 Non-Prod
Future Request
PROD 0/1
—
26
monday.com
×1 Instance
×1 Prod
×0 Non-Prod
Not Started
PROD 0/1
—
27
Asana
×1 Instance
×1 Prod
×0 Non-Prod
Not Started
PROD 0/1
—
28
Jira Service Mgmt
×2 Instance
×2 Prod
×2 Non-Prod
Onboarding In Progress
PROD 1/2
NP 0/2
29
Freshdesk
×1 Instance
×1 Prod
×0 Non-Prod
Not Started
PROD 0/1
—
30
Intercom
×1 Instance
×1 Prod
×0 Non-Prod
Future Request
PROD 0/1
—
NOTE
Status Grouping: Completed = 'Completed' + 'De-Scoped' (shown in green). Pending = 'Onboarding In Progress' + 'Not Started' + 'Future Request' (shown with their respective colour). Status is determined by the JIRA dropdown field configured in config.py → STATUS_FIELD.
[ Add your org footer here ]

## Slide 11
SSPM Initiative | Phase 2 Applications — Integration Status
P2 · Pg 6/6
Instance Coverage
PROD
7/52
NON-PROD
0/26
App Status Breakdown
2 Done
7 In Prog
18 Not Strt
5 Future
#
Application · Org / Prod / Non-Prod Instances
Status
PROD
NON-PROD
31
Twilio
×2 Instance
×2 Prod
×0 Non-Prod
Not Started
PROD 0/2
—
32
SendGrid
×1 Instance
×1 Prod
×0 Non-Prod
Completed
PROD 0/1
—
NOTE
Status Grouping: Completed = 'Completed' + 'De-Scoped' (shown in green). Pending = 'Onboarding In Progress' + 'Not Started' + 'Future Request' (shown with their respective colour). Status is determined by the JIRA dropdown field configured in config.py → STATUS_FIELD.
[ Add your org footer here ]

## Slide 12
SSPM Initiative | Blockers & Impediments
5 Blockers
Active Blockers & Impediments
B1
Salesforce EMEA — Prod tenant access pending IT Ops approval
Phase 1
Owner: IT Ops
High
B2
ServiceNow NA — API endpoint unreachable, firewall change raised
Phase 1
Owner: Network
High
B3
Workday NA — Non-Prod tenant config not shared by app owner
Phase 1
Owner: App Owner
Med
B4
Box EMEA — Licence procurement approval pending Finance sign-off
Phase 2
Owner: Finance
Med
B5
Atlassian — Prod API key rotation blocking SSPM connector config
Phase 2
Owner: Platform
High
[ Add your org footer here ]

## Slide 13
SSPM Initiative | Milestones & Roadmap
Phase 2 · Auto-Ticketing Integration
In Progress
1
SSPM → ServiceNow connector: requirements & design
Completed
2
Connector build — Phase 1 apps (P1 scope)
Completed
3
Connector build — Phase 2 apps (P2 scope)
In Progress
4
Ticket template design (fields, SLA, priority rules)
In Progress
5
Assignment routing rules & escalation matrix
Not Started
6
UAT — internal SSPM team validation
Not Started
7
UAT — app owner pilot (10 apps)
Not Started
8
Runbook: auto-ticket lifecycle SOP
Not Started
9
Load & performance testing
Not Started
10
Go-live & hypercare (2-week window)
Not Started
Phase 3 · Scorecard & Operationalisation
Not Started
1
Define KPIs and scoring framework
Not Started
2
Build SSPM health dashboard (Power BI / Tableau)
Not Started
3
App owner reporting template & cadence
Not Started
4
Runbook & SOP documentation
Not Started
5
SSPM operating model (BAU) sign-off
Not Started
[ Add your org footer here ]

## Slide 14
SSPM Initiative | Milestones & Roadmap
Pg 2
Phase 3 · Scorecard & Operationalisation (continued)
6
BAU handover to operations team
Not Started
7
Post-go-live review & lessons learned
Not Started
8
Hypercare exit criteria & sign-off
Not Started
Phase 4 · Continuous Improvement & Expansion
Not Started
1
Review Phase 3/4 app onboarding backlog
Not Started
2
Automated risk-scoring model v2
Not Started
3
Integration with PAM / IAM tooling
Not Started
4
Expanded SSPM coverage: Phase 4 apps (198 apps)
Not Started
5
Quarterly review cadence with steering committee
Not Started
6
Audit & compliance reporting package
Not Started
[ Add your org footer here ]

## Slide 15
SSPM Initiative | Appendix — Application Instance Detail
Pg 1/8
#
Application
Instance
App ID
Phase
Env
Sub-task Key
Status
1
Salesforce
Salesforce - APAC Prod
—
Phase 1
Prod
SSPM-101-P1
Completed
2
Salesforce
Salesforce - APAC Prod
—
Phase 1
Non-Prod
SSPM-101-NP1
Completed
3
Salesforce
Salesforce - APAC DR
—
Phase 1
Prod
SSPM-102-P1
Completed
4
Salesforce
Salesforce - APAC DR
—
Phase 1
Non-Prod
SSPM-102-NP1
Not Started
5
Salesforce
Salesforce - EMEA Prod
—
Phase 1
Prod
SSPM-103-P1
Not Started
6
Salesforce
Salesforce - EMEA Prod
—
Phase 1
Non-Prod
SSPM-103-NP1
Not Started
7
Salesforce
Salesforce - Japan Prod
—
Phase 1
Prod
SSPM-104-P1
Completed
8
Salesforce
Salesforce - Japan Prod
—
Phase 1
Non-Prod
SSPM-104-NP1
Completed
9
Salesforce
Salesforce - NA Prod
—
Phase 1
Prod
SSPM-105-P1
Completed
10
Salesforce
Salesforce - NA Prod
—
Phase 1
Non-Prod
SSPM-105-NP1
Not Started
11
Salesforce
Salesforce - NA Sandbox
—
Phase 1
Prod
SSPM-106-P1
Not Started
12
Salesforce
Salesforce - NA Sandbox
—
Phase 1
Non-Prod
SSPM-106-NP1
Not Started
13
Salesforce
Salesforce - Global Prod
—
Phase 1
Prod
SSPM-107-P1
Completed
14
Salesforce
Salesforce - TG Prod
—
Phase 1
Prod
SSPM-108-P1
Not Started
15
Workday
Workday - APAC Prod
—
Phase 1
Prod
SSPM-201-P1
Completed
16
Workday
Workday - APAC Prod
—
Phase 1
Non-Prod
SSPM-201-NP1
Completed
17
Workday
Workday - EMEA Prod
—
Phase 1
Prod
SSPM-202-P1
Completed
18
Workday
Workday - EMEA Prod
—
Phase 1
Non-Prod
SSPM-202-NP1
Not Started
19
Workday
Workday - NA Prod
—
Phase 1
Prod
SSPM-203-P1
Not Started
20
Workday
Workday - NA Prod
—
Phase 1
Non-Prod
SSPM-203-NP1
Not Started
[ Add your org footer here ]

## Slide 16
SSPM Initiative | Appendix — Application Instance Detail
Pg 2/8
#
Application
Instance
App ID
Phase
Env
Sub-task Key
Status
21
ServiceNow
ServiceNow - APAC Prod
—
Phase 1
Prod
SSPM-301-P1
Completed
22
ServiceNow
ServiceNow - APAC Prod
—
Phase 1
Non-Prod
SSPM-301-NP1
Completed
23
ServiceNow
ServiceNow - EMEA Prod
—
Phase 1
Prod
SSPM-302-P1
Completed
24
ServiceNow
ServiceNow - EMEA Prod
—
Phase 1
Non-Prod
SSPM-302-NP1
Not Started
25
ServiceNow
ServiceNow - NA Prod
—
Phase 1
Prod
SSPM-303-P1
Not Started
26
ServiceNow
ServiceNow - NA Prod
—
Phase 1
Non-Prod
SSPM-303-NP1
Not Started
27
ServiceNow
ServiceNow - Japan Prod
—
Phase 1
Prod
SSPM-304-P1
Completed
28
GitHub Enterprise
GitHub Ent - APAC
—
Phase 1
Prod
SSPM-401-P1
Completed
29
GitHub Enterprise
GitHub Ent - APAC
—
Phase 1
Non-Prod
SSPM-401-NP1
Completed
30
GitHub Enterprise
GitHub Ent - EMEA
—
Phase 1
Prod
SSPM-402-P1
Completed
31
GitHub Enterprise
GitHub Ent - EMEA
—
Phase 1
Non-Prod
SSPM-402-NP1
Completed
32
GitHub Enterprise
GitHub Ent - NA
—
Phase 1
Prod
SSPM-403-P1
Not Started
33
GitHub Enterprise
GitHub Ent - NA
—
Phase 1
Non-Prod
SSPM-403-NP1
Not Started
34
Microsoft 365
M365 - APAC Prod
—
Phase 1
Prod
SSPM-501-P1
Completed
35
Microsoft 365
M365 - EMEA Prod
—
Phase 1
Prod
SSPM-502-P1
Completed
36
Microsoft 365
M365 - Japan Prod
—
Phase 1
Prod
SSPM-503-P1
Completed
37
Microsoft 365
M365 - NA Prod
—
Phase 1
Prod
SSPM-504-P1
Not Started
38
Microsoft 365
M365 - Global Prod
—
Phase 1
Prod
SSPM-505-P1
Not Started
39
Okta
Okta - APAC Prod
—
Phase 1
Prod
SSPM-601-P1
Completed
40
Okta
Okta - APAC Prod
—
Phase 1
Non-Prod
SSPM-601-NP1
Completed
[ Add your org footer here ]

## Slide 17
SSPM Initiative | Appendix — Application Instance Detail
Pg 3/8
#
Application
Instance
App ID
Phase
Env
Sub-task Key
Status
41
Okta
Okta - NA Prod
—
Phase 1
Prod
SSPM-602-P1
Completed
42
Okta
Okta - NA Prod
—
Phase 1
Non-Prod
SSPM-602-NP1
Completed
43
Okta
Okta - EMEA Prod
—
Phase 1
Prod
SSPM-603-P1
Not Started
44
Okta
Okta - EMEA Prod
—
Phase 1
Non-Prod
SSPM-603-NP1
Not Started
45
Zoom
Zoom - Global Prod
—
Phase 1
Prod
SSPM-701-P1
Completed
46
Zoom
Zoom - Global Prod
—
Phase 1
Non-Prod
SSPM-701-NP1
Not Started
47
Zoom
Zoom - Japan Prod
—
Phase 1
Prod
SSPM-702-P1
Not Started
48
Slack
Slack - Global Prod
—
Phase 1
Prod
SSPM-801-P1
Completed
49
Slack
Slack - APAC Prod
—
Phase 1
Prod
SSPM-802-P1
Not Started
50
Slack
Slack - APAC Prod
—
Phase 1
Non-Prod
SSPM-802-NP1
Not Started
51
Palo Alto Prisma
Prisma - APAC Prod
—
Phase 1
Prod
SSPM-901-P1
Completed
52
Palo Alto Prisma
Prisma - APAC Prod
—
Phase 1
Non-Prod
SSPM-901-NP1
Completed
53
Palo Alto Prisma
Prisma - NA Prod
—
Phase 1
Prod
SSPM-902-P1
Completed
54
Palo Alto Prisma
Prisma - NA Prod
—
Phase 1
Non-Prod
SSPM-902-NP1
Not Started
55
CrowdStrike
CrowdStrike - Global
—
Phase 1
Prod
SSPM-1001-P1
Completed
56
CrowdStrike
CrowdStrike - Global
—
Phase 1
Non-Prod
SSPM-1001-NP1
Not Started
57
Proofpoint
Proofpoint - APAC
—
Phase 1
Prod
SSPM-1101-P1
Completed
58
Proofpoint
Proofpoint - EMEA
—
Phase 1
Prod
SSPM-1102-P1
Completed
59
Proofpoint
Proofpoint - NA
—
Phase 1
Prod
SSPM-1103-P1
Not Started
60
Mimecast
Mimecast - APAC Prod
—
Phase 1
Prod
SSPM-1201-P1
Not Started
[ Add your org footer here ]

## Slide 18
SSPM Initiative | Appendix — Application Instance Detail
Pg 4/8
#
Application
Instance
App ID
Phase
Env
Sub-task Key
Status
61
Mimecast
Mimecast - APAC Prod
—
Phase 1
Non-Prod
SSPM-1201-NP1
Not Started
62
Mimecast
Mimecast - EMEA Prod
—
Phase 1
Prod
SSPM-1202-P1
Not Started
63
Mimecast
Mimecast - EMEA Prod
—
Phase 1
Non-Prod
SSPM-1202-NP1
Not Started
64
Qualys
Qualys - Global Prod
—
Phase 1
Prod
SSPM-1301-P1
Completed
65
Rapid7
Rapid7 - APAC Prod
—
Phase 1
Prod
SSPM-1401-P1
Not Started
66
Rapid7
Rapid7 - NA Prod
—
Phase 1
Prod
SSPM-1402-P1
Not Started
67
Tenable
Tenable - APAC
—
Phase 1
Prod
SSPM-1501-P1
Not Started
68
Varonis
Varonis - NA Prod
—
Phase 1
Prod
SSPM-1601-P1
Not Started
69
SailPoint
SailPoint - APAC
—
Phase 1
Prod
SSPM-1701-P1
Not Started
70
SailPoint
SailPoint - APAC
—
Phase 1
Non-Prod
SSPM-1701-NP1
Not Started
71
SailPoint
SailPoint - EMEA
—
Phase 1
Prod
SSPM-1702-P1
Not Started
72
SailPoint
SailPoint - EMEA
—
Phase 1
Non-Prod
SSPM-1702-NP1
Not Started
73
BeyondTrust
BeyondTrust - Global
—
Phase 1
Prod
SSPM-1801-P1
Not Started
74
Box
Box - APAC Prod
—
Phase 2
Prod
SSPM-2001-P1
Completed
75
Box
Box - APAC Prod
—
Phase 2
Non-Prod
SSPM-2001-NP1
Not Started
76
Box
Box - EMEA Prod
—
Phase 2
Prod
SSPM-2002-P1
Not Started
77
Box
Box - EMEA Prod
—
Phase 2
Non-Prod
SSPM-2002-NP1
Not Started
78
Box
Box - NA Prod
—
Phase 2
Prod
SSPM-2003-P1
Not Started
79
Box
Box - NA Prod
—
Phase 2
Non-Prod
SSPM-2003-NP1
Not Started
80
Dropbox
Dropbox - APAC Prod
—
Phase 2
Prod
SSPM-2101-P1
Not Started
[ Add your org footer here ]

## Slide 19
SSPM Initiative | Appendix — Application Instance Detail
Pg 5/8
#
Application
Instance
App ID
Phase
Env
Sub-task Key
Status
81
Dropbox
Dropbox - NA Prod
—
Phase 2
Prod
SSPM-2102-P1
Not Started
82
Atlassian (Jira/Confluence)
Atlassian - APAC Prod
—
Phase 2
Prod
SSPM-2201-P1
Completed
83
Atlassian (Jira/Confluence)
Atlassian - APAC Prod
—
Phase 2
Non-Prod
SSPM-2201-NP1
Not Started
84
Atlassian (Jira/Confluence)
Atlassian - EMEA Prod
—
Phase 2
Prod
SSPM-2202-P1
Not Started
85
Atlassian (Jira/Confluence)
Atlassian - EMEA Prod
—
Phase 2
Non-Prod
SSPM-2202-NP1
Not Started
86
Atlassian (Jira/Confluence)
Atlassian - NA Prod
—
Phase 2
Prod
SSPM-2203-P1
Not Started
87
Atlassian (Jira/Confluence)
Atlassian - NA Prod
—
Phase 2
Non-Prod
SSPM-2203-NP1
Not Started
88
Zendesk
Zendesk - APAC Prod
—
Phase 2
Prod
SSPM-2301-P1
Not Started
89
Zendesk
Zendesk - APAC Prod
—
Phase 2
Non-Prod
SSPM-2301-NP1
Not Started
90
Zendesk
Zendesk - Global Prod
—
Phase 2
Prod
SSPM-2302-P1
Not Started
91
DocuSign
DocuSign - APAC Prod
—
Phase 2
Prod
SSPM-2401-P1
Completed
92
DocuSign
DocuSign - APAC Prod
—
Phase 2
Non-Prod
SSPM-2401-NP1
Not Started
93
DocuSign
DocuSign - NA Prod
—
Phase 2
Prod
SSPM-2402-P1
Not Started
94
DocuSign
DocuSign - NA Prod
—
Phase 2
Non-Prod
SSPM-2402-NP1
Not Started
95
HubSpot
HubSpot - APAC Prod
—
Phase 2
Prod
SSPM-2501-P1
Not Started
96
HubSpot
HubSpot - APAC Prod
—
Phase 2
Non-Prod
SSPM-2501-NP1
Not Started
97
HubSpot
HubSpot - NA Prod
—
Phase 2
Prod
SSPM-2502-P1
Not Started
98
Tableau / Salesforce Analytics
Tableau - APAC Prod
—
Phase 2
Prod
SSPM-2601-P1
Completed
99
Tableau / Salesforce Analytics
Tableau - APAC Prod
—
Phase 2
Non-Prod
SSPM-2601-NP1
Not Started
100
Tableau / Salesforce Analytics
Tableau - EMEA Prod
—
Phase 2
Prod
SSPM-2602-P1
Not Started
[ Add your org footer here ]

## Slide 20
SSPM Initiative | Appendix — Application Instance Detail
Pg 6/8
#
Application
Instance
App ID
Phase
Env
Sub-task Key
Status
101
Tableau / Salesforce Analytics
Tableau - EMEA Prod
—
Phase 2
Non-Prod
SSPM-2602-NP1
Not Started
102
Tableau / Salesforce Analytics
Tableau - NA Prod
—
Phase 2
Prod
SSPM-2603-P1
Not Started
103
Coupa
Coupa - APAC Prod
—
Phase 2
Prod
SSPM-2701-P1
Not Started
104
Coupa
Coupa - APAC Prod
—
Phase 2
Non-Prod
SSPM-2701-NP1
Not Started
105
Coupa
Coupa - NA Prod
—
Phase 2
Prod
SSPM-2702-P1
Not Started
106
Snowflake
Snowflake - APAC Prod
—
Phase 2
Prod
SSPM-2801-P1
Not Started
107
Snowflake
Snowflake - APAC Prod
—
Phase 2
Non-Prod
SSPM-2801-NP1
Not Started
108
Snowflake
Snowflake - NA Prod
—
Phase 2
Prod
SSPM-2802-P1
Not Started
109
Snowflake
Snowflake - NA Prod
—
Phase 2
Non-Prod
SSPM-2802-NP1
Not Started
110
Splunk
Splunk - Global Prod
—
Phase 2
Prod
SSPM-2901-P1
Completed
111
Splunk
Splunk - Global Prod
—
Phase 2
Non-Prod
SSPM-2901-NP1
Not Started
112
Ariba / SAP
Ariba - APAC Prod
—
Phase 2
Prod
SSPM-3001-P1
Not Started
113
Ariba / SAP
Ariba - APAC Prod
—
Phase 2
Non-Prod
SSPM-3001-NP1
Not Started
114
Ariba / SAP
Ariba - EMEA Prod
—
Phase 2
Prod
SSPM-3002-P1
Not Started
115
Ariba / SAP
Ariba - EMEA Prod
—
Phase 2
Non-Prod
SSPM-3002-NP1
Not Started
116
Veeva Vault
Veeva - APAC Prod
—
Phase 2
Prod
SSPM-3101-P1
Not Started
117
Veeva Vault
Veeva - NA Prod
—
Phase 2
Prod
SSPM-3102-P1
Not Started
118
Workiva
Workiva - Global Prod
—
Phase 2
Prod
SSPM-3201-P1
Not Started
119
NetSuite
NetSuite - APAC Prod
—
Phase 2
Prod
SSPM-3301-P1
Not Started
120
NetSuite
NetSuite - NA Prod
—
Phase 2
Prod
SSPM-3302-P1
Not Started
[ Add your org footer here ]

## Slide 21
SSPM Initiative | Appendix — Application Instance Detail
Pg 7/8
#
Application
Instance
App ID
Phase
Env
Sub-task Key
Status
121
Anaplan
Anaplan - APAC Prod
—
Phase 2
Prod
SSPM-3401-P1
Not Started
122
Concur (SAP)
Concur - Global Prod
—
Phase 2
Prod
SSPM-3501-P1
Not Started
123
Adobe Sign
Adobe Sign - APAC
—
Phase 2
Prod
SSPM-3601-P1
Not Started
124
Adobe Sign
Adobe Sign - APAC
—
Phase 2
Non-Prod
SSPM-3601-NP1
Not Started
125
Adobe Sign
Adobe Sign - NA
—
Phase 2
Prod
SSPM-3602-P1
Not Started
126
Adobe Sign
Adobe Sign - NA
—
Phase 2
Non-Prod
SSPM-3602-NP1
Not Started
127
SuccessFactors
SuccessFactors - APAC
—
Phase 2
Prod
SSPM-3701-P1
Not Started
128
SuccessFactors
SuccessFactors - EMEA
—
Phase 2
Prod
SSPM-3702-P1
Not Started
129
Darktrace
Darktrace - APAC Prod
—
Phase 2
Prod
SSPM-3801-P1
Completed
130
Darktrace
Darktrace - APAC Prod
—
Phase 2
Non-Prod
SSPM-3801-NP1
Not Started
131
Elastic (ELK)
Elastic - Global Prod
—
Phase 2
Prod
SSPM-3901-P1
Not Started
132
Elastic (ELK)
Elastic - Global Prod
—
Phase 2
Non-Prod
SSPM-3901-NP1
Not Started
133
PagerDuty
PagerDuty - Global
—
Phase 2
Prod
SSPM-4001-P1
Not Started
134
Dynatrace
Dynatrace - APAC Prod
—
Phase 2
Prod
SSPM-4101-P1
Not Started
135
Dynatrace
Dynatrace - APAC Prod
—
Phase 2
Non-Prod
SSPM-4101-NP1
Not Started
136
Dynatrace
Dynatrace - NA Prod
—
Phase 2
Prod
SSPM-4102-P1
Not Started
137
Dynatrace
Dynatrace - NA Prod
—
Phase 2
Non-Prod
SSPM-4102-NP1
Not Started
138
Miro
Miro - Global Prod
—
Phase 2
Prod
SSPM-4201-P1
Not Started
139
Figma
Figma - Global Prod
—
Phase 2
Prod
SSPM-4301-P1
Not Started
140
Notion
Notion - Global Prod
—
Phase 2
Prod
SSPM-4401-P1
Not Started
[ Add your org footer here ]

## Slide 22
SSPM Initiative | Appendix — Application Instance Detail
Pg 8/8
#
Application
Instance
App ID
Phase
Env
Sub-task Key
Status
141
monday.com
monday.com - APAC
—
Phase 2
Prod
SSPM-4501-P1
Not Started
142
Asana
Asana - Global Prod
—
Phase 2
Prod
SSPM-4601-P1
Not Started
143
Jira Service Mgmt
JSM - APAC Prod
—
Phase 2
Prod
SSPM-4701-P1
Completed
144
Jira Service Mgmt
JSM - APAC Prod
—
Phase 2
Non-Prod
SSPM-4701-NP1
Not Started
145
Jira Service Mgmt
JSM - NA Prod
—
Phase 2
Prod
SSPM-4702-P1
Not Started
146
Jira Service Mgmt
JSM - NA Prod
—
Phase 2
Non-Prod
SSPM-4702-NP1
Not Started
147
Freshdesk
Freshdesk - APAC Prod
—
Phase 2
Prod
SSPM-4801-P1
Not Started
148
Intercom
Intercom - Global
—
Phase 2
Prod
SSPM-4901-P1
Not Started
149
Twilio
Twilio - APAC Prod
—
Phase 2
Prod
SSPM-5001-P1
Not Started
150
Twilio
Twilio - NA Prod
—
Phase 2
Prod
SSPM-5002-P1
Not Started
151
SendGrid
SendGrid - Global
—
Phase 2
Prod
SSPM-5101-P1
Not Started
[ Add your org footer here ]